## Tabelle1
group | Asset | side | Appearance | Function | Processed by | Conzeptart existing | Size | Difficulty | Riquired Time | Status | Priority | deadline | Storage Location/ File Name/ File
Character | Main Character | cat left side | A white cat with light blue ears and tip of the tail. Big cute head and strong, characteristic expression. Her tail pointing upwards in a relaxed expression. | The player character is to ensure the connection between the game and the player. In addition, the cat with its cheeky, cute look supports the pleasant feeling that is to be transported through the game. With its blue cloud tail and ears, it also supports the cat's mystical abilities. The cat can run, dig, take damage, die and occupy itself while doing nothing. These images serve as a template for the animations. |  | yes | 1 | 2
|  | cat right side | "" | "" |  |  | 1 | 2
|  | cat front | "". Tail is visible centered between bouth ears above the head. | "" |  |  | 1 | 2
|  | cat back | "". Easr and back of thehead are visible. Pink arsehole is visible. | "" |  |  | 1 | 2
| Walking animation cat | left/right | simple walk cicle. A little bit clumsy for the cuteness. | The cat must be able to walk from tile to tile in all directiions with a smouth animation. |  |  | 1 | 1
|  | front | "" | "" |  |  | 1 | 1
|  | back | "" | "" |  |  | 1 | 1
| idle animation cat | left/ right | 7 Different Animations: sitting, paw up, licking, paw down, tail wiggling, laying, sleeping | When the player doesn´t move for more than 10 seconds the idle animation is initiated. The idle animation is a combination of different Sequences and loops. Every idle animation starts with the cat sitting down. After that it can eather lift ist paw, lick it and put ist paw down or wiggle ist tail. To change the position it can lay down and start sleeping until the player starts moving again. |  |  | 1 | 3
| damage animation cat | left/ right | The cat recoils and puts up its tail (as if it had received an electric shock). Its eyes are wide open and its mouth a little open (as if it were hissing). It makes a frightened impression and then returns to its starting position. (see photos of frightened cats). The colour changes briefly to a pinkish tinge and then returns to normal. In addition, she bends down a little and the buttocks go up. (as if she were ducking.) | The player should simply be able to recognise that his last action was wrong and that the character has taken damage. This should be indicated by a frightened cat and the unusual colour changes. |  |  | 1 | 1
|  | front | "" | "" |  |  | 1 | 2
|  | back | The buttocks go up a bit and the front down. The tail stands up more and the colour changes to a pinkish tinge. | "" |  |  | 1 | 2
| death animation cat | left/ right | The death animation should be calm and peaceful. The cat lies down as if going to sleep and then changes colour piece by piece as it dissolves into golden stardust starting from the ears. | The player should realise that he has made too many mistakes and that the game is now over for him. However, he should not be frustrated or stressed by this. Therefore, the cat does not die realistically, but more or less falls asleep and dissolves into stardust. This also supports the dream character of the game world. |  |  | 1 | 2
|  | front | "" | "" |  |  | 1 | 2
Enemies | enemie type 1 | front | A pale pink to rich pink ghost in the shape of a flame with an evil expression. It is said to look recognisably more aggressive than type 2. | The type 1 ghost is a traumatic memory which is not killed by the player (i.e. processed by the old woman). However, it can consume beautiful memories (polariod icons) and thus become a type 2 ghost, which can be "processed". |  | yes | 1 | 3
| Idle animation | front | Die tip of the flame move left to right as if blown by the wind. (or like the tail of a waiting cat). | -
| walking animation enemie type 1 | left/ right | Walking cicle in with the Ghost moves slightly up and down and the tips of the flames wiggle from left to right. | - |  |  | 1 | 2
|  | front | "" | - |  |  | 1 | 2
|  | back | "" | - |  |  | 1 | 2
| enemie type 2 | front | A yellowish to orange-red ghost in the shape of a flame with a negative, bored expression. Less aggressive in appearance than type 1. | The type 2 ghost is a bad memory which is not processed yet but can be dissolved. When processed (by killing it) it reveals the beautyfull memories behind it and drops a polariod icon collecible. |  | yes | 1 | 3
| Idle animation | fornt | Die tip of the flame move left to right as if blown by the wind. (or like the tail of a waiting cat). | -
| walking animation enemie type 2 | left/ right | Walking cicle in with the Ghost moves slightly up and down and the tips of the flames wiggle from left to right. | - |  |  | 1 | 2
|  | front | "" | - |  |  | 1 | 2
|  | back | "" | - |  |  | 1 | 2
| death animation enemie type 2 | front | The flame dissolves into particles until it has disappeared completely. At the same time, her facial expression becomes happy/peaceful. | By killing it or processing it, it becomes a good memory and turns into a collectible. |  |  | 1 | 2
NPCs | grandmother | right/ left |  |  |  |  | 1 | 3 |  |  | 1
| close up | right 3/4 |  |  |  |  | 2 | 3 |  |  | 2
| idle animation | right/ left |  |  |  |  | 1 | 1 |  |  | 3
| talking animation close | right/ left |  |  |  |  | 1 | 1 |  |  | 2
| middleage grandmother | right/ left |  |  |  |  | 1 | 3 |  |  | 1
| close up | right 3/4 |  |  |  |  | 2 | 3 |  |  | 2
| idle animation | right/ left |  |  |  |  | 1 | 1 |  |  | 3
| talking animation close | right/ left |  |  |  |  | 1 | 1 |  |  | 2
| young adult grandmother | right/ left |  |  |  |  | 1 | 3 |  |  | 1
| close up | right 3/4 |  |  |  |  | 2 | 3 |  |  | 2
| idle animation | right/ left |  |  |  |  | 1 | 1 |  |  | 3
| talking animation close | right/ left |  |  |  |  | 1 | 1 |  |  | 2
| teen grandmother | right/ left |  |  |  |  | 1 | 3 |  |  | 1
| close up | right 3/4 |  |  |  |  | 2 | 3 |  |  | 2
| idle animation | right/ left |  |  |  |  | 1 | 1 |  |  | 3
| talking animation close | right/ left |  |  |  |  | 1 | 1 |  |  | 2
soap bubbles | normal bubble |  | Colourfull round soap bubble with the colourrange of sorroundings, enemies and good memories. (a mixture of everything) | The normal bubble is simultaniously an enviornmental and interactive objekt as it is moveble, blocks the way and can fall downwards if the coulds underneath it have been digged away. It also fall one tile left or right downwards if the tile on ist sides are digged stright down and the could underneath is still there. |  |  | 1 | 2
| north bubbles |  | Normal bubble in bluish colours. | North bubbles can not be moved by pushing it. Fall upwards when the clouds above them have been digged away. |  | yes (normal bubble) | 1 | 1 |  |  | 1
| falling animation |  | fall animation of the normal soap bubble only in blue. | - |  |  | 1 | 1 |  |  | 2
| east bubbles |  | Normal bubble in yellowish colours. | East bubbles can not be moved by pushing it. They Fall eastwise when the clouds on their right have been digged away. |  | yes (normal bubble) | 1 | 1 |  |  | 1
| falling animation |  | fall animation of the normal soap bubble only in yellow. | - |  |  | 1 | 1 |  |  | 2
| south bubbles |  | Normal bubble in redish colours. | South bubbles can not be moved by pushing it. Fall downwards when the clouds underneath them have been digged away. |  | yes (normal bubble) | 1 | 1 |  |  | 1
| falling animation |  | fall animation of the normal soap bubble just in red. | - |  |  | 1 | 1 |  |  | 2
| west bubbles |  | Normal bubble in greenish colours. | West bubbles can not be moved by pushing it. They Fall westwise when the clouds on their left have been digged away. |  | yes (normal bubble) | 1 | 1 |  |  | 1
| falling animation |  | fall animation of the normal soap buble just in green. (Debateble because green is not in our colourweel) | - |  |  | 1 | 1 |  |  | 2
| compas | [5 empty] | 2 | 2 |  |  | 2
Tiles | block (1 Tile) |  |  | They dont fall but can be pushed in each direction. They cannot be pushed throgh or ontop of clouds. |  |  | 1 | 2 |  |  | 1
| block (2 Tiles) |  |  | "" |  |  | 1 | 2 |  |  | 1
| Walls |  | Bluish brick wall with four stones. Little detail. | The charakter shall not pass these (Gandalf demanded that … sorry) |  |  | 1 | 3
| Clouds |  | Bluish fog in the form of fluffy clouds with few, small particles. | disapear when the character walks over them or diggs them. |  |  | 1 | 2
| Door |  | Old, reinforced wooden door in frame rounded at the top in light brown tones. | Serves as a gateway into the next levle room or back into the game hub. |  |  | 1 | 2
| Door opening animation |  | The door opens into a black room. | - |  |  | 1 | 1
Polariods | Icon |  | Heavily simplified, slightly bevelled Polaroid photo in yellowish retro style. | Show the player what to collect to complete a levle and make progress. After all Icons are collected the door opens. |  |  | 1 | 2
| shine animation icon |  | A quick white shine effekt running over the picture. | emphasises the colletible and makes it more visible for the player. |  |  | 1 | 2
| Gallery picture levle 1 |  |  | Gives you hints about the backstory of the cat and the old lady. Should deepen the emotional connection between the player and the characters. |  | yes | 2 | 3 |  |  | 2
| Gallery picture levle 2 |  |  | "" |  |  | 2 | 3 |  |  | 2
| Gallery picture levle 3 |  |  | "" |  |  | 2 | 3 |  |  | 2
| Gallery picture levle 4 |  |  | "" |  |  | 2 | 3 |  |  | 2
Backgrounds | Start Screen |  | An idyllic scene of a country house with a veranda on the right and a deciduous tree with a swing on the left and an orange-yellow sunset in the background. Two levels: Country house and tree in black in the foreground (as if there was almost no light left. Only small shades.) and the coloured sunset in the background. On top of this is the logo in the middle and a lettering at the bottom of the screen centred on: "Press z to start" in light purple. | Helps setting the vibe and getting a first impression of the athmosphere and the game. For warming up. |  |  | 3 | 3
| Home Background |  | Only the background layer of the start screen with the home menu centred on the screen. |  |  |  | 3 | 2
| Ingame Background |  | A dark blue to purple night sky with stars of different sizes and shapes. It should have a calming and peaceful effect. Two large clouds are visible on either side of the screen. |  |  |  | 3 | 2
| Ingame Background animation |  | The clouds move from right to left in a barely discernible slow loop. The larger stars get bigger and smaller to create a flickering effect. |  |  |  | 2 | 2
| Game Hub background |  |  | For ingame Navigation between the levles and the Gallery. |  |  | 3 | 3 |  |  | 2
| Gallery |  |  | To rewatch the collected momories and taking some time to comprehend the story. |  | yes | 3 | 3 |  |  | 2
| guling in animation |  | The image floats above the opened photo book and falls onto the blank page when a button is pressed. It is held in place by two adhesive strips on opposite corners. It is not glued in quite straight to create a looser impression. |  |  |  | 2 | 2 |  |  | 3
| Room 0 levle 1 | [5 empty] | 3 | 3 |  |  | 2
| Room 0 level 2 | [5 empty] | 3 | 3 |  |  | 2
| Room 0 level 3 | [5 empty] | 3 | 3 |  |  | 2
| Room 0 level 4 | [5 empty] | 3 | 3 |  |  | 2
Menus | Home Menu | [5 empty] | 2 | 2
| Ingame Menu | [5 empty] | 2 | 2
| Talking Screen | [5 empty] | 2 | 1 |  |  | 2
Logo | Logo | [5 empty] | 2 | 3
| shine logo animation | [5 empty] | 2 | 1
Other | Hotbar |  |  |  |  | yes | 2 | 2 |  |  | 2
| fond | [5 empty] | - | 2 |  |  | 2
Cut scenes | Intro | [5 empty] | 3 | 3 |  |  | 3
| Outro | [5 empty] | 3 | 3 |  |  | 3
Legend
picture
animation
Diana
Tabea
Szabi
Size 1-3
1: small (1 tile)
2: medium (something inbetween)
3: big (screensize)
Difficulty 1-3
1: eazy
2: medium
3: hard
Priority 1-3
1: urgend
2: to be done
3: process when free